## Project Data
Project Name | EMBArk Orchestration Framework
Online team meeting | https://tu-berlin.zoom-x.de/j/62142983444?pwd=nnFsVt1p6bEKQRS6xN2oYewQqTlcF7.1
Production system (if any) | ...
Test system (if any) | ...
GitHub repository | https://github.com/amosproj/amos2025ss01-embark-orchestration-framework
GitHub feature board | https://github.com/orgs/amosproj/projects/79/views/2
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/83
Team T-shirt (white) | https://www.shirtinator.de/s/qaSIJh2NSBO7V5kllYTrWQ
Team T-shirt (black) | https://www.shirtinator.de/s/Bhl3o0Z8R2635N-1SYy3VA
Additional materials | ...
Team maling list | oss-amos-proj1@lists.fau.de

## Project Team
| First Name | GitHub User Name | Email Address
Kunow | Johannes | jkunow | j.kunow@tu-berlin.de
Meusling | Patrick | SirGankalot | meusling@campus.tu-berlin.de
Dekanozishvili | Luka | LukaDeka | luka.dekanozishvili1@gmail.com
Roy | Paul | PaulRoy1 | paul.roy@fau.de
Novak | Jannik | ashiven | nevisha@pm.me
Prosser | Clemens | ClProsser | clemens.prosser@gmail.com
Damm | Sönke Fridtjof | fridtjof-damm | soenke.f.damm@campus.tu-berlin.de

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | Comment | Homework Manager
1 | 2025-04-16 |  | Johannes | Everyone else | Patrick Meusling | COACH student |  | Patrick Meusling
2 | 2025-04-23 | Johannes | Fridtjof | Everyone else | Clemens Prosser | COACH student |  | Clemens Prosser
3 | 2025-04-30 | Fridtjof | Johannes | Everyone else | Clemens Prosser | COACH student |  | Clemens Prosser
4 | 2025-05-07 | Johannes | Fridtjof | Everyone else | Patrick Meusling | COACH student |  | Patrick Meusling
5 | 2025-05-14 | Fridtjof | Johannes | Everyone else | Jannik Novak | COACH student |  | Luka Dekanozishvili
6 | 2025-05-21 | Johannes | Fridtjof | Everyone else | Luka Dekanozishvili | COACH student |  | Luka Dekanozishvili
7 | 2025-05-28 | Fridtjof | Johannes | Everyone else | Luka Dekanozishvili | COACH student | Mid-term due | Johannes Kunow
8 | 2025-06-04 | Johannes | Fridtjof | Everyone else | Jannik Novak | COACH student |  | Fridtjof Damm
9 | 2025-06-11 | Fridtjof | Johannes | Everyone else | Patrick Meusling | COACH student |  | Johannes Kunow
10 | 2025-06-18 | Johannes | Fridtjof | Everyone else | Patrick Meusling | COACH student |  | Fridtjof Damm
11 | 2025-06-25 | Fridtjof | Johannes | Everyone else | Clemens Prosser | COACH student |  | Johannes Kunow
12 | 2025-07-02 | Johannes | Fridtjof | Everyone else | Clemens Prosser | COACH student |  | Fridtjof Damm
13 | 2025-07-09 | Fridtjof | Johannes | Everyone else | Luka Dekanozishvili | COACH student |  | Johannes Kunow
14 | 2025-07-16 | Johannes | Fridtjof | Everyone else | Luka Dekanozishvili | COACH student | Demo day! | Fridtjof Damm
15 | 2025-07-23 | Fridtjof |  | Everyone else | Jannik Novak | COACH student | Retrospective | Johannes Kunow
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here
Formulas:
Meeting Day = [Meeting Day, row above]+7

## Team Contract
Goals | Aquire new skills
Produce a functioning and valuable product
Meeting norms | We show up to the team meeting on time
We respect each others opinions
Working norms | Produce clean code
We respect other people's work
Coordination norms | Task responsibilities are well defined
We balance workload among the team
Communication norms | We check our communication platform at least once every workday
We communicate constructively
Consideration norms | We discuss issues openly
We vote in case we can't reach a consensus
Cont. improvement norms | We consider the happines index to monitor team motivation
We encourage critique and improvement efforts
Rewards | We praise each others work
We treat ourselfes to a sweet of choice for good work
Sanctions | 10 push-ups infront of the camera
We critize objectively
Signatures
Scrum Master | Paul Roy
Product owner | Johannes Kunow
Product owner | Fridtjof Damm
Software developer | Luka Dekanozishvili
Software developer | Jannik Novak
Software developer | Patrick Meusling
Software developer | Clemens Prosser

## Product Goal
Product Vision | Project Mission
The firmware security analyzer EMBA, along with it's management and orchstration platform EMBArk, enables security professionals and firmware analysts to automate the scalable execution of firmware security scans. This is achieved by parallelizing firmware analyses, reducing manual effort and boosting throughput. As embedded systems become increasingly ubiquitous and complex, EMBArk constitutes a key part in the critical infrastructure in responsible and scalable firmware deployment and development—positioning itself as an essential tool for secure digital transformation. These core values are supplied to users of arbitrary firmware, penetration testing departments, and device vendors, with the common goal of ensuring high security standards. | The mission of this project is to develop a functional orchestration component for EMBArk that enables scalable and automated execution of firmware analysis tasks using the existing EMBA tooling. The MVP will support managing distributed workers (Kali/Ubuntu) via SSH, provide an API interface for job creation, and enable testers to manage worker nodes through a web-based dashboard. Key deliverables include job scheduling, worker management, result collection, and system monitoring features.

## Product Glossary
Term | Definition
worker node | a vm or physical machine carrying out firmware analyses
orchestrator | component which schedules firmware analysis jobs to worker nodes
celery task queue | a python task queue to allow for concurrent processing
worker node configuring | the action of installing EMBA and all its dependencies on a worker node so that it can be used to analyse firmware

## Sprint Goals
Sprint # | Sprint goal
1 | None
2 | None
3 | Implement basic API features
4 | Establishing code quality best practices
5 | Set cornerstones for orchestration from UI, worker configuration, and scheduling perspectives
6 | Completing UI functionality and enable communication between EMBArk and worker nodes
7 | Adding core orchestrator functionality and prepare UI for future features
8 | Enable dispatching of firmware analyses with the orchestrator
9 | Tie loose orchestrator ends together
10 | Enhance worker management to refine user experience
11 | Invest in stability
12 | Finally finish main orchestrator functionality
13
14
15

## Velocity Tracking
Sprint # | Story Points Realized
1 | 0
2 | 0
3 | 9
4 | 14
5 | 22
6 | 14
7 | 7
8 | 14
9 | 9
10 | 10
11 | 8
12
13
107
PLEASE CREATE THE VELOCITY CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 51 | 51
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 |  |  | 0 | 51 | 0 | 51
2 |  |  | 0 | 51 | 0 | 51
3 | Implement basic API features |  | 9 | 51 | 9 | 51
4 | Establishing code quality best practices |  | 12 | 42 | 14 | 42
5 | Set cornerstones for orchestration from UI, worker configuration, and scheduling perspectives |  | 15 | 30 | 22 | 28
6 | Completing UI functionality and enable communication between EMBArk and worker nodes |  | 15 | 15 | 9 | 6
7
8
Features
1
2
3 | Implement basic API features
|  | API ¦ Documentation tooling | 1 |  | 1
|  | Mount file system via SSHfs in Python | 2 |  | 2
|  | API ¦ Generate API-Key in user interface | 3 |  | 3
|  | API ¦ Upload firmware and add to queue | 3 |  | 3
4 | Establishing code quality best practices
|  | Integration testing | 2 |  | 2
|  | API ¦ Documentation Upload firmware | 1 |  | 1
|  | API ¦ Get status report | 3 |  | 5
|  | API ¦ Documentation Status report | 1 |  | 1
|  | API ¦ Integration test Upload firmware | 2 |  | 2
|  | Configure worker nodes in EMBArk | 3 |  | 3
5 | Set cornerstones for orchestration from UI, worker configuration, and scheduling perspectives
|  | API ¦ Document API-Key generation | 1 |  | 1
|  | API ¦ Integration test API-Key generation | 2 |  | 2
|  | EMBA offline worker configuration | 3 |  | 5
|  | Configuration scripts for worker node ¦ Kali | 3 |  | 5
|  | Configuration scripts for worker node ¦ Ubuntu | 3 |  | 5
|  | Reduce check_project.sh execution time | 1 |  | 2
|  | API ¦ Integration test Status report | 2 |  | 2
6 | Completing UI functionality and enable communication between EMBArk and worker nodes
|  | EMBArk worker UI | 3 |  | 3
|  | Orchestrator ¦ Receive new workers | 3 |  | 3
|  | Caching in GitHub actions pipeline | 2 |  | not completed
|  | Configure worker node | 5 |  | 3
|  | Query worker node information | 2 |  | not completed
|  | Prepare upstream pull request | 2 |  | 2
|  | Connect to worker node | 2 |  | 3

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 74 | 74
Sprints
7 |  |  | 8 | 74 | 7 | 74
8 |  |  | 13 | 66 | 14 | 67
9 |  |  | 7 | 53 | 9 | 53
10 |  |  | 12 | 46 | 10 | 44
11 |  |  | 7 | 34 | 8 | 34
12 |  |  | 12 | 27 |  | 26
13 |  |  | 15 | 15
Features
7
|  | Orchestrator ¦ FIFO scheduling | 2 |  | 2
|  | EMBArk worker UI ¦ Show job id in worker nodes table | 2 |  | 1
|  | Orchestrator ¦ Query worker pool | 2 |  | 2
|  | Caching in Github actions pipeline | 2 |  | 2
8
|  | Add Celery dependency | 2 |  | 2
|  | Soft reset worker node | 2 |  | 2
|  | Periodic worker information fetch | 3 |  | 2
|  | Update worker nodes | 3 |  | 5
|  | Query worker node information | 2 |  | 2
|  | UI ¦ Update/Reset | 1 |  | 1
9
|  | Pass newly configured worker nodes to orchestrator | 1 |  | 2
|  | EMBArk starts firmware analysis on worker node | 2 |  | 3
|  | Hard reset worker node | 1 |  | 1
|  | Fix Github Actions bugs | 2 |  | 2
|  | Use Celery for worker node updates | 1 |  | 1
10
|  | Add Settings App to EMBArk | 2 |  | 2
|  | Manually check for updates | 3 |  | 3
|  | EMBArk default installation produces FileNotFoundError on startup | 2 |  | 1
|  | Collect dependency version information when configuring or updating node | 2 |  | 1
|  | Celery for reset | 1 |  | 1
|  | Add users to sudoers when configuring workers | 1 |  | 1
|  | Reset all worker nodes in config | 1 |  | 1
11
|  | Hide worker app in sidebar when disabled | 1 |  | 1
|  | Orchestrator ¦ Free worker nodes | 2 |  | 2
|  | Safe and prioritized worker update management | 1 |  | 2
|  | PR Revised Github Actions pipeline and check_project.sh | 1 |  | 1
|  | Download specific worker nodes dependency version | 2 |  | 2
12
|  | Trigger Orchestrator | 2
|  | Orchestrator ¦ Abort running firmware analysis | 2
|  | Monitor workers and collect results | 2
|  | Orchestrator ¦ Draft Upstream pull request | 2
|  | Add wiki entries for API | 1
|  | Celery for IP range scanning | 1
|  | Indicate currently installed dependency versions for EMBA and externals | 1
|  | Check EMBArk permissions | 1
13
|  | Bug fixing | 3
|  | Orchestrator PR: Change requests | 2
|  | Handle unresponsive worker nodes | 2
|  | Extend update user experience | 1
|  | Validate analysis workflow with orchestrators | 1
|  | Provide adequate feedback for apt dependency updates of worker nodes | 2
|  | Wiki entries for Orchestrator | 2
|  | Don't allow overlapping IP ranges in configurations | 1
|  | Change worker authentication to SSH Keys | 1

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done
1 | Github actions pipeline runs without errors | Features and changes have been demoed in review | Build and deployment documentation exists
2 | If changes are visible to users, documentation is added | Features not covered by unit tests are not negatively impacted by sprints changes | Software architecture documentation is up to date
3 | Code review passed |  | Readme is up to date
4 | Code merged to main branch
5 | Testable code has appropriate unit tests (Unfortunately the nature of the product forbids general statements for code coverage)
6 | SBOM updated: Added new dependencies to SBOM, removed removed dependencies
7 | Changes added to change log
8 | All added dependencies follow an open source license compatible with the project
* Upstream PR is explicitly not part of the DoD because the client prefers frequent pulls as soon as features are ready

## Documentation
Type | Link / reference

## Bill of Materials
You have to replace them where needed but otherwise I'd just not touch them any longer. | Name | Version | License | Comment
1 | daphne | 4.1.2 | BSD | python package
2 | mysqlclient | 2.2.7 | GPLv2+ | python package
3 | django-apscheduler | 0.7.0 | MIT | python package
4 | python-dotenv | 1.1.0 | BSD-3-Clause | python package
5 | Rx | 3.2.0 | MIT | python package
6 | inotify-simple | 1.3.5 | BSD | python package
7 | psutil | 7.0.0 | BSD-3-Clause | python package
8 | msgpack | 1.1.0 | Apache 2.0 | python package
9 | django | 5.2 | BSD-3-Clause | python package
10 | django-hashid-field | 3.4.1 | MIT | python package
11 | django-tables2 | 2.7.5 | BSD | python package
12 | requests | 2.32.3 | Apache 2.0 | python package
13 | djangorestframework | 3.16.0 | BSD | python package
14 | watchdog | 6.0.0 | Apache 2.0 | python package
15 | channels | 4.2.2 | BSD | python package
16 | channels-redis | 4.2.1 | BSD | python package
17 | mod-wsgi-standalone | 5.0.2 | Apache 2.0 | python package
18 | django-bootstrap5 | 25.1 | BSD-3-Clause | python package
19 | pytz | 2025.2 | MIT | python package
20 | pycodestyle | 2.13.0 | MIT | python package; development only
21 | djlint | 1.36.4 | GPLv3+ | python package; development only
22 | pylint-django | 2.6.1 | GPLv2+ | python package; development only
23 | selenium | 4.31.0 | Apache 2.0 | python package; development only
24 | EMBA | latest | MIT
25 | jquery.js | 3.6.0 | MIT | javascript library
26 | confirm.js | 3.3.2 | MIT | javascript library
27 | bootstrap.js | 5.2.3 | MIT | javascript library
28 | datatable.js | 1.11.2 | MIT | javascript library
29 | charts.js | 3.5.1 | MIT | javascript library
30 | base64.js | 3.7.5 | MIT | javascript library
31 | ansi_up.js | 6.0.2 | MIT | javascript library
32 | confirm.css | 3.3.2 | MIT | css library
33 | bootstrap.css | 5.2.3 | MIT | css library
34 | datatable.css | 1.11.2 | MIT | css library
35 | spectral | 6.15.0 | Apache 2.0 | npm package; development only
36 | paramiko | 3.5.1 | LGPL | python package
37 | celery | 5.5.3 | BSD-3-Clause | python package
38 | django-celery-beat | 2.8.1 | BSD | python package

## Planning Poker
Last Name | First Name | Value
Meusling | Patrick |  | #DIV/0! | #DIV/0!
Dekanozishvili | Luka
Novak | Jannik
Prosser | Clemens
|  |  | 0 | No size
|  |  | 1 | Trivial size
|  |  | 2 | Small size
|  |  | 3 | Medium size
|  |  | 5 | Large size
|  |  | 8 | Very large size
|  |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value